## 工作表1
Mango Image Release Flow (v1.2)
Creator: Guangwei, Jun03'13
NO# | Catalog | Action Items | PIC | Time Cost
1 | Prepare | 1.1 Get command to build new image; | Allan
|  | 1.2 List the differences between the new version and latest version, and send out the difference list to team member; | Allan
|  | 1.3 Set the deadline, and inform every function PIC to commit their patches to Git server before the deadline; | Allan
|  | 1.4 Double check all of patches have committed to Git server; (Notes: the patches should be same with the list in step 1.2) | Allan
|  | 1.5 If all of patches are OK, then change the image version and commit; If some of the patches have problem, please inform Boyce/Guangwei ASAP; | Allan
2 | Build | 2.1 Build image with automate build script "Mango_xx_release"; Notes: "xx" mean the SKU type; | Allan
|  | 2.2 Prepare the image ReleaseNotes; | Allan
|  | 2.3 Calculate the checksum of images; | Allan
|  | 2.4 Put the images/ReleaseNotes/checksum on our server, and send mail to inform team member to do test; | Allan
3 | Fixed issue verify | 3.1 Issue or patch owner, double check the issue has fixed or patch works fine; | Issue Owner
|  | 3.2 Issue or patch owner send mail to confirm the image; | Issue Owner
4 | Smoke Test | 4.1 Assign at least 2 members to do smoke test; | Allan
|  | 4.2 After complete the test, send out the smoke test report; And highlight the failed items in the mail if fail found; | Allan/Tenix
5 | Regression Test | 5.1 Assign at least 2 members to do regression test; | Allan
|  | 5.2 After complete the test, send out the regression test report; And highlight the failed items in the mail if fail found; | Allan/Tenix
6 | Release | 6.1 If everything OK, transfer the images/ReleaseNotes/TestReport to ftp; | Allan
|  | 6.2 Send the formal mail to notify factory/PM/RD the new image release; | Allan
Notes: Fixed issue verify/Smoke test/Regression test, can do at the same time.
Prepare to release image
Build image
Fixed issue veriy OK?
Smoke test OK?
Regression test OK?
Release image
YES
YES
YES
NO
NO
NO
Find root cause, and fix the bugs