## 工作表1
Mango Image Release Flow (v1.0)
Creator: Guangwei, Jun02'13
NO# | Catalog | Action Items | PIC | Time Cost
1 | Prepare | 1.1 Get command to build new image; | Allan
|  | 1.2 List the differences between the new version and latest version, and send out the difference list to team member; | Allan
|  | 1.3 Set the deadline, and inform every function PIC to commit their patches to Git server before the deadline; | Allan
|  | 1.4 Double check all of patches have committed to Git server; (Notes: the patches should be same with the list in step 1.2) | Allan
|  | 1.5 If all of patches are OK, then change the image version and commit; If some of the patches have problem, please inform Boyce/Guangwei ASAP; | Allan
2 | Build | 2.1 Build image with automate build script "Mango_xx_release"; Notes: "xx" mean the SKU type; | Allan
|  | 2.2 Prepare the image ReleaseNotes; | Allan
|  | 2.3 Calculate the checksum of images; | Allan
|  | 2.4 Put the images/ReleaseNotes/checksum on our server, and send mail to inform team member to do test; | Allan
3 | Fixed issue verify | 3.1 Issue or patch owner, double check the issue has fixed or patch works fine; | Issue Owner
|  | 3.2 Issue or patch owner send mail to confirm the image; | Issue Owner
4 | Smoke Test | 4.1 Assign at least 2 members to do smoke test; | Allan
|  | 4.2 After complete the test, send out the smoke test report; And highlight the failed items in the mail if fail found; | Allan/Tenix
5 | Regression Test | 5.1 Assign at least 2 members to do regression test; | Allan
|  | 5.2 After complete the test, send out the regression test report; And highlight the failed items in the mail if fail found; | Allan/Tenix
6 | Release | 6.1 If everything OK, transfer the images/ReleaseNotes/TestReport to ftp; | Allan
|  | 6.2 Send the formal mail to notify factory/PM/RD the new image release; | Allan